OPEN CLAW

Development Roadmap & Sprint Plan

Version 1.0  |  February 2026

# Development Phases Overview

Open Claw development is organized into four phases, each building on the last. The goal is to have a working prototype (Phase 1) as fast as possible, then iterate toward a polished product. Each phase is broken into 1-2 week sprints.

| Phase | Focus | Duration | Milestone |
| --- | --- | --- | --- |
| Phase 1 | Core Voice Loop (MVP) | 2–3 weeks | Talk to AI, hear response |
| Phase 2 | Memory + Reminders | 3–4 weeks | AI remembers you, sends reminders |
| Phase 3 | Polish & UX | 2–3 weeks | Beta-ready product |
| Phase 4 | Launch & Iterate | Ongoing | Public beta / app store |

# Phase 1: Core Voice Loop (MVP)

Goal: Get the fundamental voice interaction working end-to-end. User speaks, AI processes, AI responds with voice. This is the skeleton everything else builds on.

## Sprint 1 (Week 1–2): Backend Voice Pipeline

- Set up project repo, development environment, and Docker Compose

- Build WebSocket server (FastAPI) that accepts audio streams

- Integrate STT service (start with OpenAI Whisper API or Deepgram)

- Integrate LLM (OpenAI API or Claude API) with streaming responses

- Integrate TTS service (OpenAI TTS or ElevenLabs)

- Build streaming pipeline: audio in → STT → LLM → TTS → audio out

- Test with a simple web client (browser microphone → WebSocket → speaker)

Deliverable: A working backend that accepts audio, processes it through the full pipeline, and returns audio. Testable via browser.

## Sprint 2 (Week 2–3): Mobile App Shell

- Initialize React Native project with Expo

- Build main voice screen with push-to-talk button

- Implement audio capture and WebSocket streaming to backend

- Implement audio playback of streamed TTS response

- Add visual feedback: listening indicator, thinking state, speaking waveform

- Add basic conversation transcript view

- Test full loop: speak on phone → see transcript → hear AI response

Deliverable: A mobile app where you can have a voice conversation with AI. Basic but functional.

# Phase 2: Memory & Reminders

Goal: Make the assistant actually useful beyond single conversations. It remembers who you are and can proactively remind you of things.

## Sprint 3 (Week 3–4): Conversation Memory

- Set up PostgreSQL with pgvector extension

- Build memory extraction pipeline: after each conversation, extract key facts/preferences

- Generate embeddings for memory entries

- Before each LLM call, retrieve relevant memories via semantic search

- Inject retrieved memories into LLM system prompt

- Add memory management UI: view and delete memories

Deliverable: Tell the AI your name and preferences today, and it remembers tomorrow.

## Sprint 4 (Week 4–5): Reminder System

- Build reminder data model and CRUD API

- Implement intent detection for reminder requests using LLM function calling

- Natural language time parsing ("tomorrow at 3", "next Monday morning")

- Build reminder scheduler service (Celery + Redis)

- Push notification delivery when reminders trigger

- Spoken reminder playback: generate TTS of reminder and play it

- Add reminder list view in the app

Deliverable: Say "remind me to call the dentist tomorrow at 3" and get a spoken reminder at that time.

## Sprint 5 (Week 5–6): Authentication & User Accounts

- Implement user registration and login (email + password, or OAuth)

- JWT-based session management

- Associate conversations, memories, and reminders with user accounts

- Settings screen: voice preference, notification preferences, data management

- Data export and account deletion functionality

# Phase 3: Polish & UX

Goal: Make the app feel great. Optimize latency, polish the UI, handle edge cases, and prepare for real users.

## Sprint 6 (Week 6–7): Latency Optimization

- Profile the full voice pipeline and identify bottlenecks

- Implement speculative STT: start LLM processing on partial transcripts

- Implement TTS streaming: feed LLM tokens to TTS incrementally

- Add barge-in support: user can interrupt AI mid-response

- Connection warm-up: maintain persistent WebSocket and pre-warm API connections

- Add latency telemetry dashboard

## Sprint 7 (Week 7–8): UI Polish & Edge Cases

- Design and implement polished voice interaction screen (animations, transitions)

- Handle poor network conditions gracefully (offline mode, reconnection)

- Handle noisy environments (noise cancellation, confidence thresholds)

- Add onboarding flow for new users

- Accessibility review (VoiceOver/TalkBack compatibility)

- Error handling and user-friendly error messages throughout

# Phase 4: Launch & Iterate

Goal: Get real users, collect feedback, and build the features that matter most.

## Sprint 8+ (Week 8+): Beta Launch

- TestFlight (iOS) and internal testing track (Android) deployment

- Invite 20–50 beta testers

- Set up analytics: session length, feature usage, latency metrics, crash reports

- Feedback collection mechanism in-app

- Iterate based on feedback: prioritize bugs and top-requested features

- Prepare App Store / Play Store listings and submit for review

# Stretch Features (Post-Launch)

- Multiple voice/personality options for the AI

- Calendar integration (Google Calendar, Apple Calendar)

- Smart home integration (HomeKit, Google Home)

- Location-based reminders

- Conversation summaries and daily briefings

- Wake word activation ("Hey Claw")

- Multi-language support

- Desktop companion app

- Apple Watch / wearable support